## Slide 1
NA2
Aims and Challenges
WP Leader: Thomas von Rintelen, MfN
WP Deputies: Sue Ryder & Gavin Broad, NHM
SYNTHSYS 3 Final Meeting, London, 6-7 June 2017

## Slide 2
Summary of NA2
Improving collections management and enhancing accessibility
Main idea: To provide a coherent, integrated management approach that will enable NH collections to meet the expanding needs of Users, with particular focus on the development of and access to virtual and new physical collections.
Objective 1: Managing new (virtual and physical) collections
Objective 2: Developing strategic priorities for molecular related NH collections
Objective 3: Develop Collections Self-Assessment Tool (CSAT) for new collections
Kick-off meeting December 2013: Reality check and works plans
Partners:
MfN, NHM; RBGK, RBGE, MNHN, UCPH, CSIC, NRM, NCB, BGBM, NHMW, RMCA, RBINS, NMP

## Slide 3
NA2 – Tasks and responsibilities
 | Description | Due date | Objective / Task Leader
Obj 1 | Managing new (virtual and physical) collections | Aug 16 | C. Quaisser
Task 1.1 | Develop policies for virtual CM and integrate JRA outputs | Dec 15 | C. Quaisser
Task 1.2 | Produce handbook of best practice and standards for 3D imaging of NH specimens | Apr 16 | A. Kroupa
Task 1.3 | Develop policies for new physical CM | Dec 15 | O. Seberg
Obj 2 | Developing strategic priorities for molecular related NH collections | Oct 16 | R. Dekker
Task 2.1 | Develop strategic priorities for barcoding of NH collections | Dec 15 | R. Dekker
Task 2.2 | Develop strategic priorities for DNA library creation of NH collections | Aug 15 | T. von Rintelen
Task 2.3 | Develop protocols for data collection from DNA extraction | Oct 16 | I. Rey
Task 2.4 | Establish network of DNA and tissue banks | Feb 15 | O. Seberg
Obj 3 | Develop Collections Self-Assessment Tool (CSAT) for new collections | Dec 16 | R. Huxley
Task 3.1 | Collections Self Assessment provision | Aug 15 | R. Huxley
Task 3.2 | Integration of new CM approaches into the CSAT | Dec 16 | R. Huxley
JRA
JRA

## Slide 4
NA2 – Tasks and responsibilities
 | Description | Due date | Objective / Task Leader
Obj 1 | Managing new (virtual and physical) collections | Aug 16 | C. Quaisser
Task 1.1 | Develop policies for virtual CM and integrate JRA outputs | Dec 15 | C. Quaisser
Task 1.2 | Produce handbook of best practice and standards for 3D imaging of NH specimens | Apr 16 | A. Kroupa
Task 1.3 | Develop policies for new physical CM | Dec 15 | O. Seberg
Obj 2 | Developing strategic priorities for molecular related NH collections | Oct 16 | R. Dekker
Task 2.1 | Develop strategic priorities for barcoding of NH collections | Dec 15 | R. Dekker
Task 2.2 | Develop strategic priorities for DNA library creation of NH collections | Aug 15 | T. von Rintelen
Task 2.3 | Develop protocols for data collection from DNA extraction | Oct 16 | I. Rey
Task 2.4 | Establish network of DNA and tissue banks | Feb 15 | O. Seberg
Obj 3 | Develop Collections Self-Assessment Tool (CSAT) for new collections | Dec 16 | R. Huxley,
Task 3.1 | Collections Self Assessment provision | Aug 15 | R. Huxley
Task 3.2 | Integration of new CM approaches into the CSAT | Dec 16 | R. Huxley
Task 1.3 in Objective 1 merged with Task 2.4 in Objective 2 (deviation from DoW)

## Slide 5
Progress towards milestones and deliverables
Deliverable No. | Deliverable Description | Linked to Task | Due date of Deliverable | Deliverable Owner
D2.1 | "Virtual Collections" management Policy meeting: Meeting to discuss virtual collection management policies | 1.1 | Dec 2015 | Christiane Quaisser
D2.2 | "Virtual Collections" management Policy: Finalised policy for virtual collection management available | 1.1 | Aug 2016 | Christiane Quaisser
D2.3 | New physical CM policy meeting: Meeting to discuss new physical collections management policies | 1.3 / 2.4 | Dec 2015 | Ole Seberg #
D2.4 | Best practise handbook: Handbook on best practise in 3D imaging for natural history collections. | 1.2 | Apr 2016 | Jonathan Kroupa
D2.5 | New physical collections policy: Finalised policy for new physical collections management available | 1.3 / 2.4 | Dec 2015 | Ole Seberg #
D2.6 | Strategic priorities for barcoding: Report on the strategic priorities for barcoding of natural history collections | 2.1 | Dec 2015 | René Dekker
D2.7 | DNA Library construction workshop: Workshop on the construction of DNA libraries | 2.2 | Aug 2015 | Thomas von Rintelen
D2.8 | Protocols for DNA extraction: Protocols for DNA extraction made available | 2.3 | Oct 2015 | Isabel Rey
D2.9 | Updated CSAT tool: Updated Collections Self Assessment Tool (CSAT) launched | 3.2 | Dec 2016 | Rob Huxley
MS28 | Network of DNA & tissue banks established: Remit of network agreed | 2.4 | Feb 2015 | Ole Seberg
MS29 | CSAT utilisation: Minimum of 10 institutions have used CSAT | 3.1 | Aug 2015 | Robn Huxley

## Slide 6
NA2 – Workplans
 | MAIN TASK (sub task) | Who | End date
1.1 | Develop policies for virtual CM and integrate JRA outputs | CQ | 
1.1.1 | Meet with JRA Objective 4 | CQ + EH + VS | Feb 2014  Feb 2015
1.1.2 | Collect existing policies | MfN | Sep 2014  Jul 2015
1.1.3 | Discuss first summary of existing policies | MfN | Sep 2014  Jul 2015
1.1.4 | Summarise results and discussion and identify external experts needed for further advice on specific fields |  | Apr 2015  Oct 2015
1.1.5 | Meeting with CPB and additional experts | CQ | Dec 2015  Oct 2015
1.1.6 | Produce recommendations incl. IPR and international regulations | ? | Aug 2016
D2.2
D2.1

## Slide 7
NA2 – Tasks and responsibilities
 | Description | Due date | Objective / Task Leader
Obj 1 | Managing new (virtual and physical) collections | Aug 16 | C. Quaisser
Task 1.1 | Develop policies for virtual CM and integrate JRA outputs | Dec 15 | C. Quaisser
Task 1.2 | Produce handbook of best practice and standards for 3D imaging of NH specimens | Apr 16 | J. Brecko (A. Kroupa)
Task 1.3 | Develop policies for new physical CM | Dec 15 | O. Seberg
Obj 2 | Developing strategic priorities for molecular related NH collections | Oct 16 | T. von Rintelen (R. Dekker)
Task 2.1 | Develop strategic priorities for barcoding of NH collections | Dec 15 | P. Hollingsworth (R. Dekker)
Task 2.2 | Develop strategic priorities for DNA library creation of NH collections | Aug 15 | T. von Rintelen
Task 2.3 | Develop protocols for data collection from DNA extraction | Oct 16 | I. Rey
Task 2.4 | Establish network of DNA and tissue banks | Feb 15 | O. Seberg
Obj 3 | Develop Collections Self-Assessment Tool (CSAT) for new collections | Dec 16 | S. Ryder (R. Huxley)
Task 3.1 | Collections Self Assessment provision | Aug 15 | S. Ryder (R. Huxley)
Task 3.2 | Integration of new CM approaches into the CSAT | Dec 16 | S. Ryder (R. Huxley)
Leadership of Objective 2 transferred from NBC (René Dekker) to MfN (Thomas von Rintelen) (corrective measure)

## Slide 8
NA2 – Tasks and responsibilities
 | Description | Due date | Objective / Task Leader
Obj 1 | Managing new (virtual and physical) collections | Aug 16 | C. Quaisser
Task 1.1 | Develop policies for virtual CM and integrate JRA outputs | Dec 16 | C. Quaisser
Task 1.2 | Produce handbook of best practice and standards for 3D imaging of NH specimens | Apr 16 | J. Brecko (A. Kroupa)
Task 1.3 | Develop policies for new physical CM | Dec 15 | O. Seberg
Obj 2 | Developing strategic priorities for molecular related NH collections | Oct 16 | T. von Rintelen (R. Dekker)
Task 2.1 | Develop strategic priorities for barcoding of NH collections | Dec 15 | P. Hollingsworth (R. Dekker)
Task 2.2 | Develop strategic priorities for DNA library creation of NH collections | Aug 15 | T. von Rintelen
Task 2.3 | Develop protocols for data collection from DNA extraction | Oct 16 | I. Rey
Task 2.4 | Establish network of DNA and tissue banks | Feb 15 | O. Seberg
Obj 3 | Develop Collections Self-Assessment Tool (CSAT) for new collections | Dec 16 | S. Ryder (R. Huxley, P. Wilkie)
Task 3.1 | Collections Self Assessment provision | Aug 15 | S. Ryder (R. Huxley, P. Wilkie)
Task 3.2 | Integration of new CM approaches into the CSAT | Dec 16 | S. Ryder (R. Huxley, P. Wilkie)

## Slide 9
Progress towards Milestones and deliverables
Deliverable No. | Deliverable Description | Linked to Task | Due date of Deliverable | Deliverable Owner
D2.1 | "Virtual Collections" management Policy meeting: Meeting to discuss virtual collection management policies | 1.1 | Dec 2015 | Christiane Quaisser
D2.2 | "Virtual Collections" management Policy: Finalised policy for virtual collection management available | 1.1 | Aug 2016 Nov 2014 | Christiane Quaisser
D2.3 | New physical CM policy meeting: Meeting to discuss new physical collections management policies | 1.3 / 2.4 | Dec 2015 Nov 2014 | Ole Seberg
D2.4 | Best practise handbook: Handbook on best practise in 3D imaging for natural history collections. | 1.2 | Apr 2016 June 2016 | Jonathan Kroupa
D2.5 | New physical collections policy: Finalised policy for new physical collections management available | 1.3 / 2.4 | Dec 2015 Nov 2014 | Ole Seberg
D2.6 | Strategic priorities for barcoding: Report on the strategic priorities for barcoding of natural history collections | 2.1 | Dec 2015 August 2016 | Peter Hollingsworth
D2.7 | DNA Library construction workshop: Workshop on the construction of DNA libraries | 2.2 | Aug 2015 Feb 2016 | Thomas von Rintelen
D2.8 | Protocols for DNA extraction: Protocols for DNA extraction made available | 2.3 | Oct 2016 Dec 2016 | Isabel Rey
D2.9 | Updated CSAT tool: Updated Collections Self Assessment Tool (CSAT) launched | 3.2 | Dec 2016 Aug 2015 | Sue Ryder
MS28 | Network of DNA & tissue banks established: Remit of network agreed | 2.4 | Feb 2015 | Ole Seberg
MS29 | CSAT utilisation: Minimum of 10 institutions have used CSAT | 3.1 | Aug 2015 Aug 2016 | Sue Ryder

## Slide 10
Main achievements and results to date
Objective 1
Online handbook of “Collections Management Policies on Digital Data” established
Handbook and wiki to describe different 3D technologies
Objective 2
DNA barcoding priorities for NH collections established; exploration of NGS options
Explore integration of DNA library metadata into GGBN
Network of DNA & tissue banks established: integration into GGBN (Global Genome Biodiversity Network)
Objective 3
CSAT benchmarks and scoring system updated
Website upgraded
Reports (where relevant) uploaded to SYNTHESYS website

## Slide 11
Challenges
Parts of DoW outdated at start of project (DNA bank network)
Plans and responsibilities adjusted at beginning of project
Effecting partner spend and involvement > underspend addressed at later stage
Additional subtasks to incorporate new developments during project mitigating part of the underspend problem
Ability to commit time by objective/task/deliverable owners
Adjustments in responsibilities and/or time schedule
Less involvement of partners than projected
Hiring of dedicated staff
Task/deliverable owners retire/leave
Adjustments in responsibilities and/or time schedule
Lack of dedication by some partners
Less involvement of partners than projected

## Slide 12
Where to go from here
TAF Access including non EU
Staff exchange & Training
Quantification of collection richness (Big 13 initiative)
Identification and audit of orphan collections
Bring our knowledge to other institutions outside and inside Europe
Investigate networks with institutes in biodiversity hotspots including digital repatriation
Automated georeferencing
Pilot project to link collections for eTaxonomy using the output of S3
Citizen science projects (more focussed and networked)
Digital storage
Cypernetwork
Knowledge repatriation
Pipelines for collections not yet been included and inaccessible, e.g. spirit & orphan collections
Crowdsourcing
Developing CSAT further, bringing in policy documentation and align with other international initiatives such as Join the Dots
Molecular collections, NGS, DNA Libraries and archiving & linking with existing knowledge platforms, document libraries etc.
ABS and Nagoya application
GGBN development?
Create a workshop to update new partners – should happen prior to the start date of the project
Investigate UN options and collaboration
Linking data
Archive and cultural data
Citizen science e.g. climate change and distribution
Applied pilot projects in citizen science which include societal challenges
Georeferencing collections
Synchronised and coordinated data capture
CSAT development, global standard and accreditation (look at ISBER Self Assessment tool)
Evaluation of infrastructures, e.g. Leibnitz evaluation
Smithsonian assessment example, including relevance of collections, visitors, loans etc., uniqueness
Extend the CSAT from condition focussed to broader, including institutional evaluation
New communities, agriculture, medical, (similar to SciCol), education, schools programmes, social and cultural, eLearning
Collaborate with GRBIO, GRSciCol

## Slide 13
Where to go from here
Policies/guidelines/priorities/assessment for/of new and classical collections
Coordinated application of these instruments across the consortium
Coordination of content generation across institutions to meet user demands:
Digitization & georeferencing
DNA Barcoding etc
One-stop approach to making data available: one data portal